## Sheet1
| February |  | March |  |  |  | April
Task | 2nd Week | 3rd Week | 1st Week | 2nd Week | 3rd Week | 4th Week | 1st Week | 2nd Week | 3rd Week | 4th Week
Meet with Leo and Sir Migs to clarify and finalize specifications
Adjust initial parts of the paper
Create general pages for the different functionalities of the system (At least the flow of the site)
Convert created site to use codeigniter
Populate database
View list of all alumni
View logs
Basic Search **Note: requested adjustment use fulltext search
Drag and Drop
Pagination bug fix
Sort by column
Ban/Unban Staff Account
Set a staff as an admin
Export/Clear logs
Drag and Drop Templates and string representation
Google Maps
Walkthrough
View alumni profile
Homepage info
Finalization of Functionalities
Final Adjustments
Paper Finalization